## Executive Dashboard
KYC AGENTIC AI — EXECUTIVE PERFORMANCE DASHBOARD
AI Product Manager: Krishna Agrawal · PwC Netherlands · Production Pilot Q2 2024 · Tier-1 Dutch Bank
| ONBOARDING TIME | MANUAL EFFORT ↓ | DAILY VOLUME | ESCALATION RATE | AUTO-APPROVE | FALSE NEG. RATE | SYSTEM UPTIME | ANALYST CSAT
ACTUAL | 15 min | −40% | 10,247 | 16% | 84% | 1.4% | 99.7% | 88%
TARGET | ≤ 15 min | ≥ −27% | ≥ 10,000 | 15–18% | 82–85% | ≤ 1.5% | ≥ 99.5% | ≥ 80%
STATUS | ✓ Met | ✓ Met | ✓ Met | ✓ Met | ✓ Met | ✓ Met | ✓ Met | ✓ Met
WEEKLY PERFORMANCE TREND — Production Pilot (8 Weeks)
Week | Applications | Auto-Approved | Escalated | Escalation % | Avg Latency (s) | Extraction Acc % | CSAT Score | False Neg % | Analyst Overrides | P95 Latency (s) | Uptime %
1 | 487 | 392 | 95 | 19.5% | 72 | 95.8% | 78 | 1.9% | 12 | 88 | 99.2%
2 | 612 | 503 | 109 | 17.8% | 68 | 96.2% | 80 | 1.7% | 10 | 85 | 99.4%
3 | 891 | 745 | 146 | 16.4% | 65 | 96.9% | 82 | 1.6% | 9 | 83 | 99.6%
4 | 1204 | 1022 | 182 | 15.1% | 62 | 97.1% | 84 | 1.5% | 8 | 81 | 99.7%
5 | 1876 | 1590 | 286 | 15.2% | 61 | 97.3% | 85 | 1.4% | 7 | 80 | 99.8%
6 | 2241 | 1905 | 336 | 15.0% | 59 | 97.4% | 87 | 1.4% | 6 | 79 | 99.9%
7 | 1987 | 1671 | 316 | 15.9% | 58 | 97.5% | 88 | 1.3% | 5 | 78 | 99.7%
8 | 949 | 793 | 156 | 16.4% | 57 | 97.3% | 88 | 1.4% | 6 | 79 | 99.7%
AGENT PERFORMANCE SUMMARY
Agent | Purpose | Avg Confidence | Accuracy | P95 Latency (s) | Escalation Trigger % | Model Version | Last Retrained
Agent 1 — Document Ingestion | OCR + LLM field extraction | 0.94 | 97.3% | 6.2s | 4.1% | v1.3 | Q2 2024
Agent 2 — Identity Verification | Cross-reference + discrepancy | 0.91 | 96.1% | 8.7s | 5.8% | v1.2 | Q2 2024
Agent 3 — AML / Risk Scoring | PEP/sanctions + LLM risk | 0.88 | 95.4% | 18.3s | 6.2% | v1.1 | Q2 2024
Orchestrator (LangGraph) | Routing + aggregation + HITL | 0.92 | — | 2.1s | — | v2.0 | Q2 2024
ESCALATION REASON BREAKDOWN — Pilot Total (1,626 escalated cases)
Escalation Reason | Count | % of Escalations | Avg Analyst Review (min) | Override Rate | Action Taken
Low doc extraction confidence (<0.90) | 487 | 30.0% | 7.2 | 12% | Re-extract or request new doc
Identity verification confidence <0.85 | 312 | 19.2% | 8.1 | 18% | Manual cross-reference
AML risk score ≥ 0.65 (amber flag) | 284 | 17.5% | 11.3 | 8% | Compliance escalation
PEP/sanctions list potential match | 198 | 12.2% | 14.6 | 22% | Compliance escalation
Document expiry within 30 days | 176 | 10.8% | 4.2 | 3% | Customer notification
Data discrepancy (>2 fields) | 169 | 10.4% | 9.7 | 15% | Customer clarification

## OKR Tracker
OKR TRACKER — KYC AGENTIC AI · Q1–Q3 2024
Owner: Krishna Agrawal · PwC Netherlands · Last Updated: Q2 2024
OBJECTIVE 1 — Reduce Customer Onboarding Time
Key Result | Baseline | Target | Q1 Result | Q2 Result | Pilot Result | Status | Owner | Priority | Notes
KR1.1: Avg onboarding time ≤15 min | 48 hours | ≤15 min | — | 32 min | 15 min | ✓ Met | Engineering | P0 | Target exceeded in pilot
KR1.2: p95 processing latency ≤90s | N/A | ≤90s | — | 104s | 79s | ✓ Met | Engineering | P0 | Optimised in Sprint 6
KR1.3: Customer drop-off rate <10% | 23% | <10% | — | — | 8.4% | ✓ Met | PM | P1 | Measured post-pilot
OBJECTIVE 2 — Reduce Manual Analyst Effort
Key Result | Baseline | Target | Q1 Result | Q2 Result | Pilot Result | Status | Owner | Priority | Notes
KR2.1: Analyst time per app ≤27 min | 45 min | ≤27 min | — | 36 min | 27 min | ✓ Met | PM | P0 | Exactly at target
KR2.2: HITL escalation rate 15–18% | 100% manual | 15–18% | — | 19.5% | 16.0% | ✓ Met | Engineering | P0 | Stable in weeks 4–8
KR2.3: Auto-approve accuracy ≥99% | N/A | ≥99% | — | — | 99.1% | ✓ Met | Data Science | P1 | FN rate 1.4%
OBJECTIVE 3 — Achieve Regulatory Compliance & Approval
Key Result | Baseline | Target | Q1 Result | Q2 Result | Pilot Result | Status | Owner | Priority | Notes
KR3.1: Risk committee approval | Rejected (3x) | Approved | Doc prep | Presentation | Approved ✓ | ✓ Met | PM | P0 | First agentic AI approved
KR3.2: All EU AI Act Art. 9–15 met | 0/7 complete | 7/7 complete | 4/7 | 6/7 | 7/7 | ✓ Met | PM + Legal | P0 | DPO sign-off complete
KR3.3: GDPR data residency verified | Unverified | 100% EU | Architecture | DPO review | Verified | ✓ Met | Engineering + DPO | P0 | Network egress audit passed
KR3.4: False negative rate ≤1.5% | 1.8% manual | ≤1.5% | — | — | 1.4% | ✓ Met | Data Science | P0 | Below target

## Sprint Velocity
SPRINT VELOCITY & BACKLOG TRACKING — 8 SPRINTS
Sprint | Sprint Goal | Stories Planned | Stories Completed | Velocity (pts) | Completion % | Bugs Found | Bugs Resolved | Carry-over | Sprint | Velocity (pts)
S1–S2 | Discovery & Compliance scoping | 18 | 17 | 89 | 94% | 0 | 0 | 1 | S1 | 89
S3–S4 | Agent 1 Document Ingestion MVP | 24 | 22 | 112 | 92% | 3 | 3 | 2 | S2 | 112
S5–S6 | Agents 2+3 + LangGraph integration | 31 | 28 | 141 | 90% | 5 | 4 | 3 | S3 | 141
S7 | Risk committee prep + compliance audit | 14 | 14 | 71 | 100% | 1 | 1 | 0 | S4 | 71
S8 | Production pilot (500 apps) | 16 | 15 | 78 | 94% | 2 | 2 | 1 | S5 | 78
TOTAL / AVG | All 8 sprints | 103 | 96 | 491 | 93.2% | 11 | 10 | 7

## Risk Register
RISK REGISTER — KYC AGENTIC AI PRODUCT
Risk ID | Risk Description | Category | Likelihood | Impact | Risk Score | Mitigation | Owner | Status
R-001 | Model confidence miscalibrated — over-approving risky apps | Model Risk | Medium | High | HIGH | Monthly calibration review; 5% post-audit sample; weekly FN monitoring | PM + Data Science | Open
R-002 | GDPR breach via PII in LLM prompt logs | Data Privacy | Low | High | MEDIUM | PII scrubbing middleware; log audit in CI/CD; DPO sign-off | Engineering | Mitigated
R-003 | Risk committee delays approval past pilot deadline | Governance | Medium | Medium | MEDIUM | Bi-weekly check-ins; compliance lead in sprint reviews; pre-agreed checklist | PM | Closed
R-004 | Sanctions DB latency causes p95 SLA breach | Technical | Medium | Medium | MEDIUM | Async screening with provisional hold; cached results for low-risk | Engineering | Mitigated
R-005 | Analyst resistance to AI-assisted workflow | Change Mgmt | Medium | Low | LOW | Co-design sessions; volunteer pilot group; change management training | PM + UX | Closed
R-006 | Document extraction fails on non-standard ID formats | Technical | Low | Medium | LOW | Fallback to full HITL on extraction confidence <0.70; expand test set | Engineering | Open
R-007 | LangSmith logging outage breaks audit trail | Technical | Low | High | MEDIUM | Redundant logging to internal store; audit trail never depends on single system | Engineering | Mitigated
R-008 | EU AI Act requirements change pre-launch | Regulatory | Low | High | MEDIUM | Legal counsel monitoring; 2-sprint buffer in roadmap for compliance updates | Legal + PM | Open

## Market Sizing
MARKET SIZING ANALYSIS — AI-POWERED KYC AUTOMATION (EU BANKING)
Research basis: Gartner AI in Banking 2023 · EBA Digital Finance Outlook · internal PwC FS benchmarks · ECB Banking Supervision data
ADDRESSABLE MARKET ANALYSIS
Market Segment | Definition | Est. Size (€M) | CAGR | Key Driver | Assumption | Source / Confidence
TAM — Global KYC Automation | All AI-powered KYC, AML and onboarding globally | €8,400M | 14.2% | Regulatory pressure + cost reduction mandate across all banking markets | Global banking sector, all asset sizes | Gartner 2023 / High confidence
SAM — EU Regulated Banking AI KYC | EU-domiciled banks (ECB supervised + national) deploying KYC automation | €1,240M | 16.8% | EU AI Act compliance requirement accelerating investment in governed AI systems | EEA banks >€1B assets | ECB SSM data 2023 / Medium confidence
SOM — NL + DACH Tier-1 Banks (5yr) | Netherlands + Germany + Austria + Switzerland Tier-1 banks (12 institutions) | €186M | 18.4% | PwC existing relationships + KYC agent reference case drives pipeline | 12 Tier-1 institutions, avg €15.5M each | PwC internal pipeline / Medium confidence
COMPETITIVE LANDSCAPE — AI KYC AUTOMATION
Competitor / Approach | Type | EU AI Act Ready? | Agentic AI? | HITL Design | Estimated Cost | PwC Differentiator
Traditional RPA (UIPath, Blue Prism) | RPA Vendor | No | No | None | €200–800K setup | Agentic reasoning; handles document variability
KOFAX / Appian KYC Modules | Legacy FinTech | Partial | No | Basic | €500K–2M | LLM-native; explainable decisions; Art. 14 compliant
ComplyAdvantage + manual process | Data Provider | No | No | Full manual | €150–400K/yr | End-to-end automation; 48h → 15min transformation
Big 4 AI teams (McKinsey, Accenture) | Consultancy | Yes | Partial | Yes | €2–8M | Faster delivery (8 sprints); existing NL bank relationships
PwC KYC Agentic AI (this product) | Consultancy AI PM | Yes — Full | Yes — LangGraph | Full HITL | €600K–1.5M | REFERENCE CASE: First EU AI Act approved agentic KYC